## HEY Q4 PII 16-17
Performance in Initiating Clinical Research (clinical trials given C&C between 01 July 2017 and 30 June 2018)
REC Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and date Site Confirmed | Duration between date Site Confirmed and First Patient | Duration between VRA and First Patient | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
18/NW/0514 | 249725 | HRA | "SELECT - Semaglutide effects on cardiovascular outcomes in people with overweight or obesity" | 2018-08-01 | Yes | 2019-03-12 | 175 | 48 | 223 | 2018-06-01 | 2018-08-01 | 2019-01-03 | 2019-01-18 | 2019-01-23 | 2019-02-25 | Sponsor
17/EE/0347 | 201505 | HRA | A phase II randomised placebo controlled double blinded trial of Interleukin 1 blockade in Acute Severe Colitis | 2018-07-16 | Yes | 2018-11-08 | 94 | 21 | 115 | 2018-07-16 | 2018-07-16 | 2017-10-17 | 2018-10-08 | 2018-10-18 | 2018-11-08 | NHS Provider
17/EE/0361 | 231209 | HRA | A 2-treatment epoch, randomized, placebo-controlled, multicenter parallel-group study to assess the safety of QAW039 when added to existing asthma therapy in patients with uncontrolled severe asthma | 2018-07-25 | Yes | 2019-01-31 | 93 | 97 | 190 | 2018-07-09 | 2018-07-25 | 2017-10-31 | 2018-10-25 | 2018-10-26 | 2019-01-09 | Sponsor
17/SC/0532 | 232887 | HRA | A randomised, double-blind, placebo-controlled study, in COPD patients with and without a confirmed respiratory virus infection assessing anti-viral biomarker responses of inhaled SNG001 compared to placebo. | 2018-07-09 | Yes | 2019-01-13 | 86 | 102 | 188 | 2018-07-05 | 2018-07-09 | 2018-04-13 | 2018-09-25 | 2018-10-03 | 2018-10-11 | Sponsor
17/WM/0248 | 213348 | HRA | Preventing cardiac damage in patients treated for breast cancer: a phase 3 Randomised, Open label, blinded endpoint, trial of enalapril to prevent Anthracycline-induced CardioToxicity (PROACT). | 2018-07-25 | Yes | 2019-05-08 | 117 | 170 | 287 | 2018-07-25 | 2018-07-25 | 2017-08-09 | 2018-11-06 | 2018-11-19 | 2019-03-25 | Sponsor
17/YH/0269 | 228372 | HRA | A Prospective, Open, Non-Comparative Multicentre Study to Evaluate a Fibrous Silver Dressing (DURAFIBER™ Ag) in the Treatment of Moderate to Highly Exuding Venous Leg Ulcers | 2018-07-30 | No |  | 30 |  |  | 2018-07-17 | 2018-07-30 | 2017-08-25 | 2018-08-22 | 2018-08-29 | 2018-09-12 | Neither
18/SC/0242 | 238151 | HRA | A phase III randomised controlled trial of continuous beta-lactam infusion compared with intermittent beta-lactam dosing in critically ill patients. | 2018-08-24 | Yes | 2019-06-16 | 159 | 137 | 296 | 2018-07-10 | 2018-08-24 | 2018-08-24 | 2019-01-04 | 2019-01-30 | 2019-03-14 | Sponsor
18/SC/0334 | 248606 | HRA | The effect of patient positioning on patient reported outcomes after GON block for primary headache disorder; a multi-centre, four-arm, controlled, prospective randomised trial | 2018-08-01 | Yes | 2018-12-28 | 42 | 107 | 149 | 2018-06-12 | 2018-08-01 | 2018-06-19 | 2018-09-12 | 2018-09-12 | 2018-10-03 | Please Select...
18/SC/0371 | 231957 | HRA | A Two-Year, Three-Arm, Randomized, Double-Masked,Multicenter, Phase III Study assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Diabetic Macular Oedema | 2018-07-06 | Yes | 2018-11-23 | 63 | 77 | 140 | 2018-06-21 | 2018-07-06 | 2018-08-17 | 2018-08-02 | 2018-09-07 | 2018-09-27 | Sponsor
18/EE/0296 | 250366 | HRA | A Phase I, Open Label, Randomized, Parallel Group, Multicentre study to Compare the Effect of AZD9977 and Spironolactone on Serum Potassium [sK+] during 28 days in Patients with HFmrEF or HFpEF and eGFR in the range of =40 and =70 mL/min/1.73m2 | 2018-10-09 | No |  | 148 |  |  | 2018-09-20 | 2018-10-09 | 2019-01-18 | 2019-02-21 | 2019-03-06 | 2019-03-15 | Neither
15/NW/0545 | 156861 | HRA | "DexEnceph: A pragmatic, randomised, controlled, observer­blind trial comparing clinical outcomes in adults who receive dexamethasone alongside standard treatment versus standard treatment alone for Herpes Simplex Virus encephalitis." | 2018-11-22 | No |  | 144 |  |  | 2018-09-18 | 2018-11-22 | 2016-06-15 | 2019-04-09 | 2019-04-15 |  | NHS Provider
17/EM/0440 | 230556 | HRA | DANTE: A randomised phase III trial to evaluate the Duration of ANti-PD1 monoclonal antibody Treatment in patients with metastatic mElanoma | 2018-10-23 | No |  | 128 |  |  | 2018-10-23 | 2018-10-23 | 2018-01-18 | 2019-01-18 | 2019-02-28 | 2019-04-15 | Neither
18/EM/0190 | 243165 | HRA | A Phase 3, Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel-group Study to Investigate the Efficacy and Safety of CSL112 in Subjects with Acute Coronary Syndrome | 2018-07-26 | No |  | 138 |  |  | 2018-07-20 | 2018-07-26 | 2018-09-14 | 2018-11-20 | 2018-12-11 | 2019-01-21 | Neither
18/LO/0165 | 224726 | HRA | POLEM: Avelumab plus 5-FU based chemotherapy as adjuvant treatment for stage 3 MSI-High or POLE exonuclease domain mutant colon cancer: A phase 3 randomised study. | 2018-11-01 | No |  | 182 |  |  | 2018-01-12 | 2018-11-01 | 2018-05-09 | 2019-04-05 | 2019-05-02 | 2019-05-16 | Sponsor
18/LO/0612 | 235872 | HRA | CLEAR SYNERGY (OASIS 9): A 2x2 factorial randomized controlled trial of CoLchicine and spironolactonE in patients with ST elevation myocARdial infarction/SYNERGY Stent Registry – Organization to Assess Strategies for Ischemic Syndromes 9 | 2018-08-14 | Yes | 2018-11-28 | 84 | 22 | 106 | 2017-10-20 | 2018-08-14 | 2018-07-16 | 2018-09-26 | 2018-11-06 | 2018-11-20 | NHS Provider
18/LO/0997 | 216343 | HRA | Brain Imaging to predict Toxicity in Elderly patients after Radiotherapy | 2018-10-30 | Yes | 2019-01-30 | 16 | 76 | 92 | 2018-10-02 | 2018-10-30 | 2018-06-28 | 2018-10-30 | 2018-11-15 | 2019-01-14 | Sponsor
18/LO/1854 | 251689 | HRA | A Phase 3, randomized, double-blind clinical study of pembrolizumab (MK-3475) plus chemotherapy versus placebo plus chemotherapy as first-line treatment in participants with HER2 negative, previously untreated, unresectable or metastatic gastric or gastroesophageal junction adenocarcinoma (KEYNOTE-859) | 2018-11-13 | Yes | 2019-03-19 | 64 | 62 | 126 | 2018-11-13 | 2018-11-13 | 2018-12-18 | 2019-01-09 | 2019-01-16 | 2019-03-04 | NHS Provider
18/NE/0194 | 242874 | HRA | A Randomized, Double-blind, Placebo-controlled, Parallel-group, Multicenter Study to Evaluate the Effects of Sotagliflozin on Clinical Outcomes in HemodynamIcally Stable Patients with Type 2 Diabetes Post Worsening Heart Failure | 2018-09-10 | No |  | 63 |  |  | 2018-07-04 | 2018-09-10 | 2018-08-13 | 2018-10-16 | 2018-11-12 | 2019-01-24 | Neither
18/NE/0296 | 248487 | HRA | CArvediloL versus variceal Band ligation in primary pREvention of variceal bleeding in liver cirrhosis | 2018-11-28 | Yes | 2019-01-25 | 41 | 17 | 58 | 2018-11-28 | 2018-11-28 | 2018-10-19 | 2018-12-13 | 2019-01-08 | 2019-01-17 | Please Select...
18/SS/0131 | 248427 | HRA | A Randomised Controlled Trial to investigate the effectiveness of ThOracic Epidural and Paravertebral Blockade In reducing Chronic Post- Thoracotomy Pain: 2 | 2018-11-06 | Yes | 2019-02-14 | 62 | 38 | 100 | 2018-11-06 | 2018-11-06 | 2018-11-15 | 2018-12-06 | 2019-01-07 | 2019-01-09 | Please Select...
18/NW/0098 | 242717 | HRA | Two-part, double-blind, placebo-controlled, randomized, parallel-group study: (Part 1) in healthy male subjects to assess safety and tolerability of ascending repeated oral doses of BAY 1902607 including its effect on the pharmacokinetics of a sub-therapeutic dose of midazolam (MDZ), followed by (Part 2) a two-way crossover administration of four different doses of BAY 1902607 in patients with refractory chronic cough to assess safety, tolerability and efficacy for proof of concept | 2018-12-06 | Yes | 2019-04-12 | 69 | 58 | 127 | 2018-12-29 | 2018-12-06 | 2018-05-10 | 2019-02-11 | 2019-02-13 | 2019-03-13 | Please Select...
18/SC/0155 | 236211 | HRA | A multicentre international randomized parallel group double-blind placebo-controlled clinical trial of EMPAgliflozin once daily to assess cardio-renal outcomes in patients with chronic KIDNEY disease | 2018-11-12 | No |  | 134 |  |  | 2018-11-08 | 2018-11-12 | 2018-04-26 | 2019-03-15 | 2019-03-26 | 2019-05-20 | Both
18/SC/0412 | 250170 | HRA | A Phase III, Randomized, Double-blind Trial Comparing Trastuzumab Plus Chemotherapy and Pembrolizumab With Trastuzumab Plus Chemotherapy and Placebo as First-line Treatment in Participants With HER2 Positive Advanced Gastric or Gastroesophageal Junction Adenocarcinoma (KEYNOTE 811) | 2018-09-05 | Yes | 2019-02-20 | 84 | 84 | 168 | 2018-05-14 | 2018-09-05 | 2018-10-08 | 2018-10-31 | 2018-11-28 | 2018-11-29 | Sponsor
18/SS/0112 | 249816 | HRA | Evidence Generation for the Clinical Efficacy and Cost Effectiveness of MYCOPD in patients with mild, moderate and newly diagnosed COPD. | 2018-10-01 | Yes | 2018-11-14 | 37 | 7 | 44 | 2018-08-23 | 2018-10-01 | 2018-09-24 | 2018-11-06 | 2018-11-07 | 2018-11-09 | Please Select...
18/SW/0039 | 229163 | HRA | Induction of labour for predicted macrosomia | 2018-07-04 | Yes | 2019-04-30 | 154 | 146 | 300 | 2018-05-01 | 2018-07-04 | 2018-03-20 | 2018-11-23 | 2018-12-05 | 2019-02-21 | Sponsor
18/YH/0017 | 231431 | HRA | Improving the safety and continuity of medicines management at care transitions | 2018-10-05 | Yes | 2019-02-28 | 42 | 104 | 146 | 2018-10-01 | 2018-10-05 | 2018-03-01 | 2018-11-14 | 2018-11-16 | 2019-02-25 | Sponsor
18/EM/0391 | 256669 | HRA | Feasibility Study of Early Outpatient Review and Early Cardiac Rehabilitation After Coronary Artery Bypass Grafting: Mixed Methods Research Design. | 2018-12-18 | Yes | 2019-06-05 | 92 | 77 | 169 | 2018-12-07 | 2018-12-18 | 2019-03-12 | 2019-03-19 | 2019-03-20 | 2019-03-20 | Neither
15/WM/0268 | 180518 | HRA | Randomised, open label study of rituximab/ibrutinib vs rituximab/chemotherapy in older patients with untreated mantle cell lymphoma | 2018-10-15 | Yes | 2019-06-10 | 177 | 61 | 238 | 2018-10-15 | 2018-10-15 | 2016-08-26 | 2019-04-10 | 2019-04-10 | 2019-05-14 | NHS Provider
16/YH/0157 | 204585 | HRA | "PLATO - PersonaLising Anal cancer radioTherapy dOse - Incorporating Anal Cancer Trials (ACT) ACT3, ACT4 and ACT5" | 2019-01-15 | Yes | 2019-04-17 | 21 | 71 | 92 | 2019-01-15 | 2019-01-15 | 2016-07-20 | 2019-01-22 | 2019-02-05 | 2019-03-13 | Please Select...
17/WS/0147 | 184216 | HRA | PRECISION-Panc: Advancing personalised medicine treatment strategies for pancreatic cancer. | 2019-01-08 | No |  | 92 |  |  | 2019-01-08 | 2019-01-08 | 2018-01-05 | 2019-03-06 | 2019-04-10 | 2019-06-01 | Neither
18/EM/0310 | 239782 | HRA | C-Stich2: Emergency Cervical Cerclage to Prevent Miscarriage and Preterm Birth: a Randomised Controlled Trial | 2019-02-28 | No |  | 47 |  |  | 2018-12-12 | 2019-02-28 | 2018-11-16 | 2019-03-27 | 2019-04-16 | 2019-04-17 | Neither
18/LO/1186 | 236886 | HRA | PREvention of STroke in Intracerebral haemorrhaGE survivors with Atrial Fibrillation (PRESTIGE-AF) | 2018-11-27 | No |  | 126 |  |  | 2018-06-27 | 2018-11-27 | 2018-12-07 | 2019-03-14 | 2019-04-02 | 2019-07-11 | Sponsor
18/LO/2067 | 253346 | HRA | A Phase 2 Study of INCMGA00012 in Participants With Squamous Carcinoma of the Anal Canal Who Have Progressed Following Platinum-Based Chemotherapy | 2018-11-05 | Yes | 2019-05-02 | 108 | 70 | 178 | 2018-09-07 | 2018-11-05 | 2019-01-07 | 2019-02-13 | 2019-02-21 | 2019-02-22 | Neither
18/NE/0379 | 248465 | HRA | A Phase 2 Study of INCMGA00012 in Participants With Metastatic Merkel Cell Carcinoma | 2019-02-20 | No |  | 78 |  |  | 2018-12-13 | 2019-02-20 | 2018-12-21 | 2019-04-09 | 2019-05-09 | 2019-05-13 | Please Select...
18/NI/0224 | 256190 | HRA | "A Phase II Randomized, Multi-Center, Double-Blind, Global Study to Determine the Efficacy and Safety of Durvalumab plus Olaparib Combination Therapy Compared with Durvalumab Monotherapy as Maintenance Therapy in Patients whose Disease has not Progressed Following Standard of Care Platinum-Based Chemotherapy with Durvalumab in First-Line Stage IV Non-Small Cell Lung Cancer (ORION)" | 2018-12-04 | No |  | 149 |  |  | 2018-12-04 | 2018-12-04 | 2019-03-06 | 2019-04-08 | 2019-05-02 | 2019-05-07 | Sponsor
18/WA/0005 | 223997 | HRA | Phase III study assessing the “best of” radiotherapy compared to the “best of” surgery (trans-oral surgery (TOS) in patients with T1-T2, N0 oropharyngeal squamous cell carcinoma (OPSCC) | 2018-08-09 | No |  | 179 |  |  | 2018-06-25 | 2018-08-09 | 2018-03-12 | 2018-11-15 | 2019-02-04 | 2019-02-28 | NHS Provider
18/WM/0383 | 252607 | HRA | A phase 3 study investigating the efficacy, safety, and tolerability of tralokinumab administered to adult subjects with severe atopic dermatitis who are not adequately controlled with or have contraindications to oral cyclosporine A. | 2018-12-21 | Yes | 2019-05-07 | 115 | 22 | 137 | 2018-11-21 | 2018-12-21 | 2019-02-06 | 2019-04-10 | 2019-04-15 | 2019-04-23 | Please Select...
18/WS/0201 | 251717 | HRA | A 52-week, placebo-controlled, randomized, Phase 3 study to evaluate the safety and efficacy of seladelpar in subjects with primary biliary cholangitis (PBC) and an inadequate response to or an intolerance to ursodeoxycholic acid (UDCA) | 2018-12-14 | No |  | 122 |  |  | 2018-06-19 | 2018-12-14 | 2019-02-21 | 2019-04-08 | 2019-04-15 | 2019-04-17 | Sponsor
18/YH/0414 | 252888 | HRA | A study to evaluate the potential benefits of pre-operative nutritional supplements CalBisc and FitaBisc in patients undergoing elective general surgery | 2019-01-21 | No |  |  |  |  | 2018-08-15 | 2019-01-21 | 2019-01-18 |  |  |  | Sponsor
19/EE/0095 | 259908 | HRA | "A Phase 4 long-term follow-up study to define the safety profile of radium-223 dichloride" | 2019-03-27 | No |  | 77 |  |  | 2019-03-27 | 2019-03-27 | 2019-05-28 | 2019-06-10 | 2019-06-12 |  | Sponsor
19/EM/0101 | 260487 | HRA | Randomized, Double-Blind, Placebo-Controlled, Dose-Ranging, Efficacy and Safety Study with Inhaled RVT-1601 for the Treatment of Persistent Cough in Patients with Idiopathic Pulmonary Fibrosis (IPF): SCENIC Trial | 2019-03-14 | No |  |  |  |  | 2019-03-13 | 2019-03-14 | 2019-05-20 |  |  |  | NHS Provider
19/LO/0515 | 261604 | HRA | Semaglutide cardiovascular outcomes trial in patients with type 2 diabetes (SOUL) | 2019-03-05 | No |  |  |  |  | 2019-01-08 | 2019-03-05 |  |  |  |  | Sponsor
19/NE/0044 | 239218 | HRA | Hair Cycle Modulation to Promote Human Wound Healing | 2019-02-19 | Yes | 2019-07-26 | 44 | 113 | 157 | 2019-02-19 | 2019-02-19 | 2019-04-02 | 2019-04-04 | 2019-04-04 | 2019-04-04 | Please Select...
19/NW/0181 | 260431 | HRA | "A Randomized, Double-blind, Placebo-Controlled, Crossover, Dose Escalation Study of BLU-5937 in Subjects with Unexplained or Refractory Chronic Cough (RELIEF)" | 2019-03-29 | No |  |  |  |  | 2019-03-29 | 2019-03-29 |  |  |  |  | NHS Provider
19/SW/0041 | 260477 | HRA | A Phase 3, multicenter, randomized, open-label trial to compare the efficacy and safety of pembrolizumab (MK-3475) in combination with lenvatinib (E7080/MK-7902) versus docetaxel in previously treated participants with metastatic non-small cell lung cancer (NSCLC) and progressive disease (PD) after platinum doublet chemotherapy and immunotherapy (anti-PD-1/PD-L1 inhibitor) (LEAP-008) | 2019-03-15 | No |  |  |  |  | 2019-01-30 | 2019-03-15 |  |  |  |  | NHS Provider
17/LO/1509 | 232288 | HRA | A phase 3 randomised, double blind, clinical trial investigating the effectiveness of repurposed simvastatin compared to placebo, in secondary progressive multiple sclerosis, in slowing the progression of disability | 2018-11-28 | Yes | 2019-04-17 | 119 | 21 | 140 | 2018-10-04 | 2018-11-28 | 2018-01-19 | 2019-03-20 | 2019-03-27 | 2019-03-29 | Please Select...
16/EM/0322 | 202096 | HRA | A randomised-controlled trial of thrombolytic treatment with tenecteplase for acute ischaemic stroke upon awakening | 2019-01-22 | No |  | 142 |  |  | 2019-01-21 | 2019-01-22 | 2017-08-18 | 2019-05-31 | 2019-06-13 |  | Sponsor
16/ES/0110 | 207747 | HRA | Treatment of Osteogenesis Imperfecta with Parathyroid hormone and Zoledronic acid | 2019-04-02 | No |  |  |  |  | 2019-04-02 | 2019-04-02 | 2017-01-12 |  |  |  | NHS Provider
17/WS/0142 | 221370 | HRA | PRIMUS 001 - An adaptive phase II study of FOLFOX-A (FOLFOX and nab-paclitaxel) versus AG (nab-paclitaxel and gemcitabine) in patients with metastatic pancreatic cancer, with integrated biomarker evaluation | 2019-03-14 | No |  | 116 |  |  | 2019-01-21 | 2019-03-14 | 2017-09-07 | 2019-06-11 | 2019-07-08 |  | NHS Provider
18/SS/0033 | 242190 | HRA | A randomised, double-blind placebo controlled trial of the effectiveness of the beta-blocker bisoprolol in preventing exacerbations of chronic obstructive pulmonary disease. | 2019-05-13 | No |  |  |  |  | 2019-03-25 | 2019-05-13 | 2018-08-09 |  |  |  | NHS Provider
18/WA/0199 | 108978 | HRA | A randomised, placebo controlled trial of azithromycin for the prevention of chronic lung disease of prematurity in preterm infants | 2019-05-08 | No |  |  |  |  | 2019-05-08 | 2019-05-08 |  |  |  |  | NHS Provider
18/WA/0337 | 248818 | HRA | TIME: Take home naloxone Intervention Multi centre Emergency setting feasibility trial | 2019-04-03 | No |  | 34 |  |  | 2019-02-26 | 2019-04-03 | 2019-01-08 | 2019-04-03 | 2019-05-07 | 2019-05-07 | Sponsor
19/EM/0047 | 257111 | HRA | A PHASE III, MULTICENTER, RANDOMIZED, DOUBLE-MASKED, ACTIVE COMPARATOR-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF FARICIMAB IN PATIENTS WITH NEOVASCULAR AGE-RELATED MACULAR DEGENERATION (TENAYA) | 2019-04-05 | Yes | 2019-07-02 | 54 | 34 | 88 | 2019-01-30 | 2019-04-05 | 2019-04-04 | 2019-05-15 | 2019-05-29 | 2019-05-31 | NHS Provider
19/NS/0101 | 245426 | HRA | Inpatient Exercise for Critical Limb Ischaemia Patients Pre and Post Major Surgery: A Proof of Concept Study (EXERCISE) | 2019-05-31 | No |  | 20 |  |  | 2019-05-23 | 2019-05-31 | 2019-06-05 | 2019-06-20 | 2019-06-20 | 2019-06-21 | Neither
19/NW/0158 | 259931 | HRA | SCIENCE Surgery or Cast for Injuries of the EpicoNdyle in Children’s Elbows:A multi-centre prospective randomised superiority trial of operative fixation versus non-operative treatment for medial epicondyle fractures of the humerus in children. | 2019-04-08 | No |  | 93 |  |  | 2019-04-05 | 2019-04-08 | 2019-03-25 | 2019-07-10 | 2019-07-10 | 2019-07-11 | Neither
19/NW/0363 | 250571 | HRA | "Protocol I4V-MC-JAJA (RA-BRIDGE) Randomized, Active-Controlled, Parallel-Group, Phase 3b/4 Study of Baricitinib in Patients with Rheumatoid Arthritis" | 2019-06-28 | No |  |  |  |  | 2019-04-02 | 2019-06-28 |  |  |  |  | Sponsor
19/SC/0073 | 246299 | HRA | Segmental Tibial fractures, reamed Intramedullary nailing versus circular Frame external Fixation - a Feasibility study | 2019-05-07 | No |  |  |  |  | 2019-04-08 | 2019-05-07 | 2019-05-02 |  |  |  | NHS Provider
19/SC/0156 | 261750 | HRA | Promoting activity in chronic obstructive pulmonary disease (COPD): Optimising high intensity interval training and technologies, a pilot study | 2019-05-01 | Yes | 2019-05-28 | 7 | 20 | 27 | 2019-03-05 | 2019-05-01 | 2019-04-30 | 2019-05-08 | 2019-05-08 | 2019-05-09 | Please Select...
19/SS/0067 | 260562 | HRA | The British Society of Endovascular Therapy ConformabLe EndoVascular Aneurysm Repair Registry | 2019-05-08 | No |  | 35 |  |  | 2019-04-30 | 2019-05-08 | 2019-05-30 | 2019-06-12 | 2019-06-12 | 2019-06-12 | Please Select...
19/YH/0026 | 256695 | HRA | A first in human, double-blind, placebo-controlled, multicentre Phase I/II study to evaluate the safety, tolerability and immune modulatory effects of MRx-4DP0004 (a lyophilised formulation of Bifidobacterium breve proprietary strain of 4D Pharma Research) in participants taking long-term control medication for their asthma | 2019-04-12 | No |  |  |  |  | 2019-04-05 | 2019-04-12 | 2019-04-09 |  |  |  | NHS Provider
19/YH/0037 | 259722 | HRA | A pilot study to determine if the Glyco Liver Profile is a suitable candidate assay for measuring liver inflammation in Non Alcoholic Steato-Hepatitis (NASH) patients | 2019-06-05 | Yes | 2019-06-28 | 6 | 17 | 23 | 2019-03-07 | 2019-06-05 | 2019-04-05 | 2019-06-11 | 2019-06-11 | 2019-06-11 | Please Select...
19/YH/0054 | 258802 | HRA | A pragmatic, multicentre, randomised controlled trial to assess the clinical and cost effectiveness of negative pressure wound therapy versus usual care for surgical wounds healing by secondary intention (SWHSI 2) | 2019-04-10 | Yes | 2019-05-15 | 27 | 8 | 35 | 2019-02-15 | 2019-04-10 | 2019-04-05 | 2019-05-07 | 2019-05-07 | 2019-05-09 | Please Select...
19/YH/0093 | 255567 | HRA | A Randomized Open-Label, Phase 1b Study of the Safety of Pirfenidone Solution for Inhalation (AP01) in Patients with Idiopathic Pulmonary Fibrosis (ATLAS Study) | 2019-04-24 | No |  |  |  |  | 2019-04-10 | 2019-04-24 | 2019-06-04 |  |  |  | NHS Provider
19/YH/0100 | 260086 | HRA | A single arm, open-label clinical trial of azithromycin in pulmonary sarcoidosis | 2019-04-30 | No |  | 35 |  |  | 2019-04-30 | 2019-04-30 | 2019-05-30 | 2019-05-30 | 2019-06-04 |  | Sponsor
17/LO/1170 | 219279 | HRA | A multi-center, double-blind, placebo-controlled Phase 2b study to evaluate the efficacy and safety of macitentan in subjects with heart failure with preserved ejection fraction and pulmonary vascular disease | 2019-01-11 | No |  | 138 |  |  | 2019-01-10 | 2019-01-11 | 2017-08-02 | 2019-05-21 | 2019-05-29 |  | Sponsor