## HEY Q4 PII 16-17
Performance in Initiating Clinical Research (clinical trials given C&C between 01 Oct 2018 and 30 Sept 2019)
REC Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and date Site Confirmed | Duration between date Site Confirmed and First Patient | Duration between VRA and First Patient | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
18/EE/0296 | 250366 | HRA | A Phase I, Open Label, Randomized, Parallel Group, Multicentre study to Compare the Effect of AZD9977 and Spironolactone on Serum Potassium [sK+] during 28 days in Patients with HFmrEF or HFpEF and eGFR in the range of =40 and =70 mL/min/1.73m2 | 2018-09-20 | Yes | 2019-09-17 | 148 | 195 | 343 | 2018-09-20 | 2018-10-09 | 2019-01-18 | 2019-02-21 | 2019-03-06 | 2019-03-15 | Neither
15/NW/0545 | 156861 | HRA | "DexEnceph: A pragmatic, randomised, controlled, observer­blind trial comparing clinical outcomes in adults who receive dexamethasone alongside standard treatment versus standard treatment alone for Herpes Simplex Virus encephalitis." | 2018-09-18 | No |  | 144 |  |  | 2018-09-18 | 2018-11-22 | 2016-06-15 | 2019-04-09 | 2019-04-15 |  | Neither
17/EM/0440 | 230556 | HRA | DANTE: A randomised phase III trial to evaluate the Duration of ANti-PD1 monoclonal antibody Treatment in patients with metastatic mElanoma | 2018-10-23 | Yes | 2019-07-30 | 128 | 152 | 280 | 2018-10-23 | 2018-10-23 | 2018-01-18 | 2019-01-18 | 2019-02-28 | 2019-04-15 | Neither
18/LO/0165 | 224726 | HRA | POLEM: Avelumab plus 5-FU based chemotherapy as adjuvant treatment for stage 3 MSI-High or POLE exonuclease domain mutant colon cancer: A phase 3 randomised study. | 2018-01-12 | No |  | 182 |  |  | 2018-01-12 | 2018-11-01 | 2018-05-09 | 2019-04-05 | 2019-05-02 | 2019-05-16 | Sponsor
18/LO/0997 | 216343 | HRA | Brain Imaging to predict Toxicity in Elderly patients after Radiotherapy | 2018-10-02 | Yes | 2019-01-30 | 16 | 76 | 92 | 2018-10-02 | 2018-10-30 | 2018-06-28 | 2018-10-30 | 2018-11-15 | 2019-01-14 | Sponsor
18/LO/1854 | 251689 | HRA | A Phase 3, randomized, double-blind clinical study of pembrolizumab (MK-3475) plus chemotherapy versus placebo plus chemotherapy as first-line treatment in participants with HER2 negative, previously untreated, unresectable or metastatic gastric or gastroesophageal junction adenocarcinoma (KEYNOTE-859) | 2018-11-13 | Yes | 2019-03-19 | 64 | 62 | 126 | 2018-11-13 | 2018-11-13 | 2018-12-18 | 2019-01-09 | 2019-01-16 | 2019-03-04 | NHS Provider
18/NE/0296 | 248487 | HRA | CArvediloL versus variceal Band ligation in primary pREvention of variceal bleeding in liver cirrhosis | 2018-11-28 | Yes | 2019-01-25 | 41 | 17 | 58 | 2018-11-28 | 2018-11-28 | 2018-10-19 | 2018-12-13 | 2019-01-08 | 2019-01-17 | Please Select...
18/SS/0131 | 248427 | HRA | A Randomised Controlled Trial to investigate the effectiveness of ThOracic Epidural and Paravertebral Blockade In reducing Chronic Post- Thoracotomy Pain: 2 | 2018-11-06 | Yes | 2019-02-14 | 62 | 38 | 100 | 2018-11-06 | 2018-11-06 | 2018-11-15 | 2018-12-06 | 2019-01-07 | 2019-01-09 | Please Select...
18/NW/0098 | 242717 | HRA | Two-part, double-blind, placebo-controlled, randomized, parallel-group study: (Part 1) in healthy male subjects to assess safety and tolerability of ascending repeated oral doses of BAY 1902607 including its effect on the pharmacokinetics of a sub-therapeutic dose of midazolam (MDZ), followed by (Part 2) a two-way crossover administration of four different doses of BAY 1902607 in patients with refractory chronic cough to assess safety, tolerability and efficacy for proof of concept | 2018-12-29 | Yes | 2019-04-12 | 69 | 58 | 127 | 2018-12-29 | 2018-12-06 | 2018-05-10 | 2019-02-11 | 2019-02-13 | 2019-03-13 | Please Select...
18/SC/0155 | 236211 | HRA | A multicentre international randomized parallel group double-blind placebo-controlled clinical trial of EMPAgliflozin once daily to assess cardio-renal outcomes in patients with chronic KIDNEY disease | 2018-11-08 | No |  | 134 |  |  | 2018-11-08 | 2018-11-12 | 2018-04-26 | 2019-03-15 | 2019-03-26 | 2019-05-20 | Neither
18/SS/0112 | 249816 | HRA | Evidence Generation for the Clinical Efficacy and Cost Effectiveness of MYCOPD in patients with mild, moderate and newly diagnosed COPD. | 2018-08-23 | Yes | 2018-11-14 | 37 | 7 | 44 | 2018-08-23 | 2018-10-01 | 2018-09-24 | 2018-11-06 | 2018-11-07 | 2018-11-09 | Please Select...
18/YH/0017 | 231431 | HRA | Improving the safety and continuity of medicines management at care transitions | 2018-10-01 | Yes | 2019-02-28 | 42 | 104 | 146 | 2018-10-01 | 2018-10-05 | 2018-03-01 | 2018-11-14 | 2018-11-16 | 2019-02-25 | Sponsor
18/EM/0391 | 256669 | HRA | Feasibility Study of Early Outpatient Review and Early Cardiac Rehabilitation After Coronary Artery Bypass Grafting: Mixed Methods Research Design. | 2018-12-07 | Yes | 2019-06-05 | 92 | 77 | 169 | 2018-12-07 | 2018-12-18 | 2019-03-12 | 2019-03-19 | 2019-03-20 | 2019-03-20 | Neither
15/WM/0268 | 180518 | HRA | Randomised, open label study of rituximab/ibrutinib vs rituximab/chemotherapy in older patients with untreated mantle cell lymphoma | 2018-10-15 | Yes | 2019-06-10 | 177 | 61 | 238 | 2018-10-15 | 2018-10-15 | 2016-08-26 | 2019-04-10 | 2019-04-10 | 2019-05-14 | NHS Provider
16/YH/0157 | 204585 | HRA | "PLATO - PersonaLising Anal cancer radioTherapy dOse - Incorporating Anal Cancer Trials (ACT) ACT3, ACT4 and ACT5" | 2019-01-15 | Yes | 2019-04-17 | 21 | 71 | 92 | 2019-01-15 | 2019-01-15 | 2016-07-20 | 2019-01-22 | 2019-02-05 | 2019-03-13 | Please Select...
17/WS/0147 | 184216 | HRA | PRECISION-Panc: Advancing personalised medicine treatment strategies for pancreatic cancer. | 2019-01-08 | Yes | 2019-09-19 | 92 | 162 | 254 | 2019-01-08 | 2019-01-08 | 2018-01-05 | 2019-03-06 | 2019-04-10 | 2019-06-01 | Neither
18/EM/0310 | 239782 | HRA | C-Stich2: Emergency Cervical Cerclage to Prevent Miscarriage and Preterm Birth: a Randomised Controlled Trial | 2018-12-12 | No |  | 47 |  |  | 2018-12-12 | 2019-02-28 | 2018-11-16 | 2019-03-27 | 2019-04-16 | 2019-04-17 | Neither
18/LO/1186 | 236886 | HRA | PREvention of STroke in Intracerebral haemorrhaGE survivors with Atrial Fibrillation (PRESTIGE-AF) | 2018-06-27 | No |  | 126 |  |  | 2018-06-27 | 2018-11-27 | 2018-12-07 | 2019-03-14 | 2019-04-02 | 2019-07-11 | Both
18/LO/2067 | 253346 | HRA | A Phase 2 Study of INCMGA00012 in Participants With Squamous Carcinoma of the Anal Canal Who Have Progressed Following Platinum-Based Chemotherapy | 2018-09-07 | Yes | 2019-05-02 | 108 | 70 | 178 | 2018-09-07 | 2018-11-05 | 2019-01-07 | 2019-02-13 | 2019-02-21 | 2019-02-22 | Neither
18/NE/0379 | 248465 | HRA | A Phase 2 Study of INCMGA00012 in Participants With Metastatic Merkel Cell Carcinoma | 2018-12-13 | No |  | 78 |  |  | 2018-12-13 | 2019-02-20 | 2018-12-21 | 2019-04-09 | 2019-05-09 | 2019-05-13 | Neither
18/NI/0224 | 256190 | HRA | "A Phase II Randomized, Multi-Center, Double-Blind, Global Study to Determine the Efficacy and Safety of Durvalumab plus Olaparib Combination Therapy Compared with Durvalumab Monotherapy as Maintenance Therapy in Patients whose Disease has not Progressed Following Standard of Care Platinum-Based Chemotherapy with Durvalumab in First-Line Stage IV Non-Small Cell Lung Cancer (ORION)" | 2018-12-04 | No |  | 149 |  |  | 2018-12-04 | 2018-12-04 | 2019-03-06 | 2019-04-08 | 2019-05-02 | 2019-05-07 | Neither
18/WM/0383 | 252607 | HRA | A phase 3 study investigating the efficacy, safety, and tolerability of tralokinumab administered to adult subjects with severe atopic dermatitis who are not adequately controlled with or have contraindications to oral cyclosporine A. | 2018-11-21 | Yes | 2019-05-07 | 115 | 22 | 137 | 2018-11-21 | 2018-12-21 | 2019-02-06 | 2019-04-10 | 2019-04-15 | 2019-04-23 | Please Select...
18/WS/0201 | 251717 | HRA | A 52-week, placebo-controlled, randomized, Phase 3 study to evaluate the safety and efficacy of seladelpar in subjects with primary biliary cholangitis (PBC) and an inadequate response to or an intolerance to ursodeoxycholic acid (UDCA) | 2018-06-19 | No |  | 122 |  |  | 2018-06-19 | 2018-12-14 | 2019-02-21 | 2019-04-08 | 2019-04-15 | 2019-04-17 | Sponsor
18/YH/0414 | 252888 | HRA | A study to evaluate the potential benefits of pre-operative nutritional supplements CalBisc and FitaBisc in patients undergoing elective general surgery | 2018-08-15 | No |  |  |  |  | 2018-08-15 | 2019-01-21 | 2019-01-18 |  |  |  | Sponsor
19/EE/0095 | 259908 | HRA | "A Phase 4 long-term follow-up study to define the safety profile of radium-223 dichloride" | 2019-03-27 | Yes | 2019-07-04 | 77 | 22 | 99 | 2019-03-27 | 2019-03-27 | 2019-05-28 | 2019-06-10 | 2019-06-12 |  | Sponsor
19/EM/0101 | 260487 | HRA | Randomized, Double-Blind, Placebo-Controlled, Dose-Ranging, Efficacy and Safety Study with Inhaled RVT-1601 for the Treatment of Persistent Cough in Patients with Idiopathic Pulmonary Fibrosis (IPF): SCENIC Trial | 2019-03-13 | No |  |  |  |  | 2019-03-13 | 2019-03-14 | 2019-05-20 |  |  |  | Sponsor
19/LO/0515 | 261604 | HRA | Semaglutide cardiovascular outcomes trial in patients with type 2 diabetes (SOUL) | 2019-01-08 | Yes | 2019-09-12 |  |  | 191 | 2019-01-08 | 2019-03-05 |  |  |  |  | Sponsor
19/NE/0044 | 239218 | HRA | Hair Cycle Modulation to Promote Human Wound Healing | 2019-02-19 | Yes | 2019-07-26 | 44 | 113 | 157 | 2019-02-19 | 2019-02-19 | 2019-04-02 | 2019-04-04 | 2019-04-04 | 2019-04-04 | Please Select...
19/NW/0181 | 260431 | HRA | "A Randomized, Double-blind, Placebo-Controlled, Crossover, Dose Escalation Study of BLU-5937 in Subjects with Unexplained or Refractory Chronic Cough (RELIEF)" | 2019-03-29 | Yes | 2019-10-17 |  |  | 202 | 2019-03-29 | 2019-03-29 |  |  |  |  | NHS Provider
19/SW/0041 | 260477 | HRA | A Phase 3, multicenter, randomized, open-label trial to compare the efficacy and safety of pembrolizumab (MK-3475) in combination with lenvatinib (E7080/MK-7902) versus docetaxel in previously treated participants with metastatic non-small cell lung cancer (NSCLC) and progressive disease (PD) after platinum doublet chemotherapy and immunotherapy (anti-PD-1/PD-L1 inhibitor) (LEAP-008) | 2019-01-30 | No |  |  |  |  | 2019-01-30 | 2019-03-15 |  |  |  |  | Sponsor
17/LO/1509 | 232288 | HRA | A phase 3 randomised, double blind, clinical trial investigating the effectiveness of repurposed simvastatin compared to placebo, in secondary progressive multiple sclerosis, in slowing the progression of disability | 2018-10-04 | Yes | 2019-04-17 | 119 | 21 | 140 | 2018-10-04 | 2018-11-28 | 2018-01-19 | 2019-03-20 | 2019-03-27 | 2019-03-29 | Please Select...
16/EM/0322 | 202096 | HRA | A randomised-controlled trial of thrombolytic treatment with tenecteplase for acute ischaemic stroke upon awakening | 2019-01-21 | No |  | 142 |  |  | 2019-01-21 | 2019-01-22 | 2017-08-18 | 2019-05-31 | 2019-06-13 |  | Neither
16/ES/0110 | 207747 | HRA | Treatment of Osteogenesis Imperfecta with Parathyroid hormone and Zoledronic acid | 2019-04-02 | No |  |  |  |  | 2019-04-02 | 2019-04-02 | 2017-01-12 |  |  |  | Sponsor
17/WS/0142 | 221370 | HRA | PRIMUS 001 - An adaptive phase II study of FOLFOX-A (FOLFOX and nab-paclitaxel) versus AG (nab-paclitaxel and gemcitabine) in patients with metastatic pancreatic cancer, with integrated biomarker evaluation | 2019-01-21 | Yes | 2019-10-17 | 116 | 101 | 217 | 2019-01-21 | 2019-03-14 | 2017-09-07 | 2019-06-11 | 2019-07-08 |  | NHS Provider
18/SS/0033 | 242190 | HRA | A randomised, double-blind placebo controlled trial of the effectiveness of the beta-blocker bisoprolol in preventing exacerbations of chronic obstructive pulmonary disease. | 2019-03-25 | No |  |  |  |  | 2019-03-25 | 2019-05-13 | 2018-08-09 |  |  |  | Sponsor
18/WA/0199 | 108978 | HRA | A randomised, placebo controlled trial of azithromycin for the prevention of chronic lung disease of prematurity in preterm infants | 2019-05-08 | Yes | 2019-10-19 |  |  | 164 | 2019-05-08 | 2019-05-08 |  |  |  |  | NHS Provider
18/WA/0337 | 248818 | HRA | TIME: Take home naloxone Intervention Multi centre Emergency setting feasibility trial | 2019-02-26 | No |  | 34 |  |  | 2019-02-26 | 2019-04-03 | 2019-01-08 | 2019-04-03 | 2019-05-07 | 2019-05-07 | Sponsor
19/EM/0047 | 257111 | HRA | A PHASE III, MULTICENTER, RANDOMIZED, DOUBLE-MASKED, ACTIVE COMPARATOR-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF FARICIMAB IN PATIENTS WITH NEOVASCULAR AGE-RELATED MACULAR DEGENERATION (TENAYA) | 2019-01-30 | Yes | 2019-07-02 | 54 | 34 | 88 | 2019-01-30 | 2019-04-05 | 2019-04-04 | 2019-05-15 | 2019-05-29 | 2019-05-31 | NHS Provider
19/NS/0101 | 245426 | HRA | Inpatient Exercise for Critical Limb Ischaemia Patients Pre and Post Major Surgery: A Proof of Concept Study (EXERCISE) | 2019-05-23 | Yes | 2019-08-03 | 20 | 44 | 64 | 2019-05-23 | 2019-05-31 | 2019-06-05 | 2019-06-20 | 2019-06-20 | 2019-06-21 | Neither
19/NW/0158 | 259931 | HRA | SCIENCE Surgery or Cast for Injuries of the EpicoNdyle in Children’s Elbows:A multi-centre prospective randomised superiority trial of operative fixation versus non-operative treatment for medial epicondyle fractures of the humerus in children. | 2019-04-05 | Yes | 2019-08-21 | 93 | 42 | 135 | 2019-04-05 | 2019-04-08 | 2019-03-25 | 2019-07-10 | 2019-07-10 | 2019-07-11 | Neither
19/NW/0363 | 250571 | HRA | "Protocol I4V-MC-JAJA (RA-BRIDGE) Randomized, Active-Controlled, Parallel-Group, Phase 3b/4 Study of Baricitinib in Patients with Rheumatoid Arthritis" | 2019-04-02 | No |  | 57 |  |  | 2019-04-02 | 2019-08-12 | 2019-08-08 | 2019-09-04 | 2019-10-08 | 2019-10-29 | Sponsor
19/SC/0073 | 246299 | HRA | Segmental Tibial fractures, reamed Intramedullary nailing versus circular Frame external Fixation - a Feasibility study | 2019-04-08 | No |  |  |  |  | 2019-04-08 | 2019-05-07 | 2019-05-02 |  |  |  | NHS Provider
19/SC/0156 | 261750 | HRA | Promoting activity in chronic obstructive pulmonary disease (COPD): Optimising high intensity interval training and technologies, a pilot study | 2019-03-05 | Yes | 2019-05-28 | 7 | 20 | 27 | 2019-03-05 | 2019-05-01 | 2019-04-30 | 2019-05-08 | 2019-05-08 | 2019-05-09 | Please Select...
19/SS/0067 | 260562 | HRA | The British Society of Endovascular Therapy ConformabLe EndoVascular Aneurysm Repair Registry | 2019-04-30 | No |  | 35 |  |  | 2019-04-30 | 2019-05-08 | 2019-05-30 | 2019-06-12 | 2019-06-12 | 2019-08-20 | Sponsor
19/YH/0026 | 256695 | HRA | A first in human, double-blind, placebo-controlled, multicentre Phase I/II study to evaluate the safety, tolerability and immune modulatory effects of MRx-4DP0004 (a lyophilised formulation of Bifidobacterium breve proprietary strain of 4D Pharma Research) in participants taking long-term control medication for their asthma | 2019-04-05 | No |  |  |  |  | 2019-04-05 | 2019-04-12 | 2019-04-09 |  |  |  | Sponsor
19/YH/0037 | 259722 | HRA | A pilot study to determine if the Glyco Liver Profile is a suitable candidate assay for measuring liver inflammation in Non Alcoholic Steato-Hepatitis (NASH) patients | 2019-03-07 | Yes | 2019-06-28 | 6 | 17 | 23 | 2019-03-07 | 2019-06-05 | 2019-04-05 | 2019-06-11 | 2019-06-11 | 2019-06-11 | Please Select...
19/YH/0054 | 258802 | HRA | A pragmatic, multicentre, randomised controlled trial to assess the clinical and cost effectiveness of negative pressure wound therapy versus usual care for surgical wounds healing by secondary intention (SWHSI 2) | 2019-02-15 | Yes | 2019-05-15 | 27 | 8 | 35 | 2019-02-15 | 2019-04-10 | 2019-04-05 | 2019-05-07 | 2019-05-07 | 2019-05-09 | Please Select...
19/YH/0093 | 255567 | HRA | A Randomized Open-Label, Phase 1b Study of the Safety of Pirfenidone Solution for Inhalation (AP01) in Patients with Idiopathic Pulmonary Fibrosis (ATLAS Study) | 2019-04-10 | No |  |  |  |  | 2019-04-10 | 2019-04-24 | 2019-06-04 |  |  |  | Sponsor
19/YH/0100 | 260086 | HRA | A single arm, open-label clinical trial of azithromycin in pulmonary sarcoidosis | 2019-04-30 | Yes | 2019-09-17 | 35 | 105 | 140 | 2019-04-30 | 2019-04-30 | 2019-05-30 | 2019-05-30 | 2019-06-04 |  | Sponsor
17/LO/1170 | 219279 | HRA | A multi-center, double-blind, placebo-controlled Phase 2b study to evaluate the efficacy and safety of macitentan in subjects with heart failure with preserved ejection fraction and pulmonary vascular disease | 2019-01-10 | No |  | 138 |  |  | 2019-01-10 | 2019-01-11 | 2017-08-02 | 2019-05-21 | 2019-05-29 |  | Neither
17/EE/0040 | 222216 | HRA | Emergency Cerclage in Twin pregnancies at Imminent Risk of Preterm Birth: an Open-Label Randomised Controlled Trial | 2019-03-29 | No |  |  |  |  | 2019-03-29 | 2019-04-01 | 2017-03-02 |  |  |  | Sponsor
17/EE/0368 | 213669 | HRA | STRESS-L: STudy into the REversal of Septic Shock with Landiolol (Beta Blockade) | 2019-07-11 | No |  | 98 |  |  | 2019-07-11 | 2019-07-18 | 2017-11-10 | 2019-10-17 | 2019-10-24 |  | Sponsor
18/EE/0356 | 250087 | HRA | A Phase 3, Randomized, Open-label Study of NKTR-214 Combined with Nivolumab Versus Nivolumab in Participants with Previously Untreated Unresectable or metastatic Melanoma | 2018-11-26 | No |  | 323 |  |  | 2018-11-26 | 2018-11-26 | 2019-01-25 | 2019-10-07 | 2019-10-15 |  | Sponsor
18/LO/1847 | 250494 | HRA | Randomized Controlled Trial of Lasmiditan Over Four Migraine Attacks | 2019-06-14 | No |  | 106 |  |  | 2019-06-14 | 2019-06-26 | 2019-05-21 | 2019-09-26 | 2019-10-10 | 2019-10-17 | NHS Provider
18/YH/0360 | 247135 | HRA | Exercise in patients with a total Coronary Occlusion (EChO) | 2019-01-29 | No |  | 69 |  |  | 2019-01-29 | 2019-01-30 | 2019-01-28 | 2019-04-09 | 2019-04-09 | 2019-04-09 | Please Select...
19/EE/0185 | 260536 | HRA | FIRST-line support for Assistance in Breathing in Children (FIRST-ABC): A master protocol of two randomised trials to evaluate the non-inferiority of high flow nasal cannula (HFNC) versus continuous positive airway pressure (CPAP) for non-invasive respiratory support in paediatric critical care | 2019-07-05 | No |  | 98 |  |  | 2019-07-05 | 2019-07-10 | 2019-07-26 | 2019-10-09 | 2019-10-16 |  | Sponsor
19/EM/0258 | 266702 | HRA | A randomised controlled trial of full milk feeds versus intravenous fluids with gradual feeding for preterm infants (30-33 weeks gestational age) | 2019-07-17 | No |  |  |  |  | 2019-07-17 | 2019-09-18 |  |  |  |  | Please Select...
19/LO/0803 | 263749 | HRA | A 12-month prospective, randomized, interventional, global, multi-center, active-controlled study comparing sustained benefit of two treatment paradigms (erenumab qm vs. oral prophylactics) in adult episodic migraine patients | 2019-06-10 | No |  |  |  |  | 2019-06-10 | 2019-06-11 | 2019-09-27 | 2019-10-12 |  |  | NHS Provider
19/NE/0152 | 260824 | HRA | "A Double-blind, Randomized, Placebo-controlled, Multicenter Study to Evaluate the Impact of Evolocumab on Major Cardiovascular Events in Patients at High Cardiovascular Risk Without Prior Myocardial Infarction or Stroke" | 2019-05-16 | No |  | 71 |  |  | 2019-05-16 | 2019-06-04 | 2019-06-18 | 2019-08-07 | 2019-08-14 | 2019-10-07 | NHS Provider
19/SC/0034 | 254823 | HRA | A Phase 3, randomized, double-blind, parallel-group, placebo controlled multicenter study to evaluate the efficacy and safety of two doses of GLPG1690 in addition to local standard of care for minimum 52 weeks in subjects with idiopathic pulmonary fibrosis. | 2019-01-24 | Yes | 2019-10-09 | 205 | 35 | 240 | 2019-01-24 | 2019-02-11 | 2019-04-29 | 2019-08-26 | 2019-09-04 | 2019-09-11 | Please Select...
19/SW/0137 | 268815 | HRA | "A Phase 3, Randomized, Open Label Study to Compare Nivolumab plus Concurrent Chemoradiotherapy (CCRT) followed by Nivolumab plus Ipilimumab or Nivolumab plus CCRT Followed by Nivolumab vs CCRT followed by Durvalumab in Previously Untreated, Locally Advanced Non-small Cell Lung Cancer (LA NSCLC)" | 2019-05-10 | No |  |  |  |  | 2019-05-10 | 2019-08-05 |  |  |  |  | Both
19/WM/0173 | 248282 | HRA | The Safety and Efficacy of Superior Rectal Artery Embolisation to Treat Haemorrhoid Disease -- A Pilot Study | 2019-07-15 | No |  |  |  |  | 2019-07-15 | 2019-07-15 |  |  |  |  | Please Select...
19/SC/0311 | 262176 | HRA | Primary Antibiotic prophylaxis using co-trimoxazole to prevent SpontanEous bacterial PeritoniTIs in Cirrhosis (ASEPTIC) Primary Antibiotic prophylaxis using co-trimoxazole to prevent SpontanEous bacterial PeritoniTIs in Cirrhosis (ASEPTIC) | 2019-06-25 | No |  | 97 |  |  | 2019-06-25 | 2019-07-17 | 2019-08-07 | 2019-10-03 | 2019-10-22 |  | NHS Provider