## HEY Q4 PII 16-17
Performance in Initiating Clinical Research (clinical trials given C&C between 01 January 2019 and 31 December 2019)
REC Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and date Site Confirmed | Duration between date Site Confirmed and First Patient | Duration between VRA and First Patient | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
16/YH/0157 | 204585 | HRA | "PLATO - PersonaLising Anal cancer radioTherapy dOse - Incorporating Anal Cancer Trials (ACT) ACT3, ACT4 and ACT5" | 2019-01-15 | Yes | 2019-04-17 | 21 | 71 | 92 | 2019-01-15 | 2019-01-15 | 2016-07-20 | 2019-01-22 | 2019-02-05 | 2019-03-13 | Please Select...
17/WS/0147 | 184216 | HRA | PRECISION-Panc: Advancing personalised medicine treatment strategies for pancreatic cancer. | 2019-01-08 | Yes | 2019-09-19 | 92 | 162 | 254 | 2019-01-08 | 2019-01-08 | 2018-01-05 | 2019-03-06 | 2019-04-10 | 2019-06-01 | Neither
18/EM/0310 | 239782 | HRA | C-Stich2: Emergency Cervical Cerclage to Prevent Miscarriage and Preterm Birth: a Randomised Controlled Trial | 2019-02-28 | No |  | 47 |  |  | 2018-12-12 | 2019-02-28 | 2018-11-16 | 2019-03-27 | 2019-04-16 | 2019-04-17 | Neither
18/NE/0379 | 248465 | HRA | A Phase 2 Study of INCMGA00012 in Participants With Metastatic Merkel Cell Carcinoma | 2019-02-20 | No |  | 78 |  |  | 2018-12-13 | 2019-02-20 | 2018-12-21 | 2019-04-09 | 2019-05-09 | 2019-05-13 | Neither
19/LO/0515 | 261604 | HRA | Semaglutide cardiovascular outcomes trial in patients with type 2 diabetes (SOUL) | 2019-03-05 | Yes | 2019-09-12 | 160 | 31 | 191 | 2019-01-08 | 2019-03-05 | 2019-07-25 | 2019-07-24 | 2019-08-12 | 2019-08-29 | Sponsor
19/NE/0044 | 239218 | HRA | Hair Cycle Modulation to Promote Human Wound Healing | 2019-02-19 | Yes | 2019-07-26 | 44 | 113 | 157 | 2019-02-19 | 2019-02-19 | 2019-04-02 | 2019-04-04 | 2019-04-04 | 2019-04-04 | Please Select...
19/NW/0181 | 260431 | HRA | "A Randomized, Double-blind, Placebo-Controlled, Crossover, Dose Escalation Study of BLU-5937 in Subjects with Unexplained or Refractory Chronic Cough (RELIEF)" | 2019-03-29 | Yes | 2019-10-17 | 132 | 70 | 202 | 2019-03-29 | 2019-03-29 | 2019-06-14 | 2019-07-25 | 2019-08-08 | 2019-08-14 | NHS Provider
19/SW/0041 | 260477 | HRA | A Phase 3, multicenter, randomized, open-label trial to compare the efficacy and safety of pembrolizumab (MK-3475) in combination with lenvatinib (E7080/MK-7902) versus docetaxel in previously treated participants with metastatic non-small cell lung cancer (NSCLC) and progressive disease (PD) after platinum doublet chemotherapy and immunotherapy (anti-PD-1/PD-L1 inhibitor) (LEAP-008) | 2019-03-15 | No |  | 222 |  |  | 2019-01-30 | 2019-03-15 | 2019-04-02 | 2019-10-15 | 2019-10-23 | 2019-10-25 | NHS Provider
16/EM/0322 | 202096 | HRA | A randomised-controlled trial of thrombolytic treatment with tenecteplase for acute ischaemic stroke upon awakening | 2019-01-22 | No |  | 142 |  |  | 2019-01-21 | 2019-01-22 | 2017-08-18 | 2019-05-31 | 2019-06-13 | 2019-08-21 | Neither
16/ES/0110 | 207747 | HRA | Treatment of Osteogenesis Imperfecta with Parathyroid hormone and Zoledronic acid | 2019-04-02 | Yes | 2019-12-04 | 132 | 114 | 246 | 2019-04-02 | 2019-04-02 | 2017-01-12 | 2019-07-04 | 2019-08-12 | 2019-10-22 | Sponsor
17/WS/0142 | 221370 | HRA | PRIMUS 001 - An adaptive phase II study of FOLFOX-A (FOLFOX and nab-paclitaxel) versus AG (nab-paclitaxel and gemcitabine) in patients with metastatic pancreatic cancer, with integrated biomarker evaluation | 2019-03-14 | Yes | 2019-10-17 | 116 | 101 | 217 | 2019-01-21 | 2019-03-14 | 2017-09-07 | 2019-06-11 | 2019-07-08 | 2019-08-26 | NHS Provider
18/WA/0337 | 248818 | HRA | TIME: Take home naloxone Intervention Multi centre Emergency setting feasibility trial | 2019-04-03 | Yes | 2019-10-23 | 34 | 169 | 203 | 2019-02-26 | 2019-04-03 | 2019-01-08 | 2019-04-03 | 2019-05-07 | 2019-05-07 | Sponsor
19/EM/0047 | 257111 | HRA | A PHASE III, MULTICENTER, RANDOMIZED, DOUBLE-MASKED, ACTIVE COMPARATOR-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF FARICIMAB IN PATIENTS WITH NEOVASCULAR AGE-RELATED MACULAR DEGENERATION (TENAYA) | 2019-04-05 | Yes | 2019-07-02 | 54 | 34 | 88 | 2019-01-30 | 2019-04-05 | 2019-04-04 | 2019-05-15 | 2019-05-29 | 2019-05-31 | NHS Provider
19/NS/0101 | 245426 | HRA | Inpatient Exercise for Critical Limb Ischaemia Patients Pre and Post Major Surgery: A Proof of Concept Study (EXERCISE) | 2019-05-31 | Yes | 2019-08-03 | 20 | 44 | 64 | 2019-05-23 | 2019-05-31 | 2019-06-05 | 2019-06-20 | 2019-06-20 | 2019-06-21 | Neither
19/NW/0158 | 259931 | HRA | SCIENCE Surgery or Cast for Injuries of the EpicoNdyle in Children’s Elbows:A multi-centre prospective randomised superiority trial of operative fixation versus non-operative treatment for medial epicondyle fractures of the humerus in children. | 2019-04-08 | Yes | 2019-08-21 | 93 | 42 | 135 | 2019-04-05 | 2019-04-08 | 2019-03-25 | 2019-07-10 | 2019-07-10 | 2019-07-11 | Neither
19/NW/0363 | 250571 | HRA | "Protocol I4V-MC-JAJA (RA-BRIDGE) Randomized, Active-Controlled, Parallel-Group, Phase 3b/4 Study of Baricitinib in Patients with Rheumatoid Arthritis" | 2019-08-12 | Yes | 2020-01-09 | 57 | 93 | 150 | 2019-04-02 | 2019-08-12 | 2019-08-08 | 2019-09-04 | 2019-10-08 | 2019-10-29 | Sponsor
19/SC/0073 | 246299 | HRA | Segmental Tibial fractures, reamed Intramedullary nailing versus circular Frame external Fixation - a Feasibility study | 2019-05-07 | No |  | 85 |  |  | 2019-04-08 | 2019-05-07 | 2019-05-02 | 2019-07-31 | 2019-07-31 | 2019-08-05 | NHS Provider
19/SC/0156 | 261750 | HRA | Promoting activity in chronic obstructive pulmonary disease (COPD): Optimising high intensity interval training and technologies, a pilot study | 2019-05-01 | Yes | 2019-05-28 | 7 | 20 | 27 | 2019-03-05 | 2019-05-01 | 2019-04-30 | 2019-05-08 | 2019-05-08 | 2019-05-09 | Please Select...
19/SS/0067 | 260562 | HRA | The British Society of Endovascular Therapy ConformabLe EndoVascular Aneurysm Repair Registry | 2019-05-08 | No |  | 35 |  |  | 2019-04-30 | 2019-05-08 | 2019-05-30 | 2019-06-12 | 2019-06-12 | 2019-08-20 | Neither
19/YH/0026 | 256695 | HRA | A first in human, double-blind, placebo-controlled, multicentre Phase I/II study to evaluate the safety, tolerability and immune modulatory effects of MRx-4DP0004 (a lyophilised formulation of Bifidobacterium breve proprietary strain of 4D Pharma Research) in participants taking long-term control medication for their asthma | 2019-04-12 | No |  | 147 |  |  | 2019-04-05 | 2019-04-12 | 2019-04-09 | 2019-09-04 | 2019-09-06 |  | Sponsor
19/YH/0037 | 259722 | HRA | A pilot study to determine if the Glyco Liver Profile is a suitable candidate assay for measuring liver inflammation in Non Alcoholic Steato-Hepatitis (NASH) patients | 2019-06-05 | Yes | 2019-06-28 | 6 | 17 | 23 | 2019-03-07 | 2019-06-05 | 2019-04-05 | 2019-06-11 | 2019-06-11 | 2019-06-11 | Please Select...
19/YH/0054 | 258802 | HRA | A pragmatic, multicentre, randomised controlled trial to assess the clinical and cost effectiveness of negative pressure wound therapy versus usual care for surgical wounds healing by secondary intention (SWHSI 2) | 2019-04-10 | Yes | 2019-05-15 | 27 | 8 | 35 | 2019-02-15 | 2019-04-10 | 2019-04-05 | 2019-05-07 | 2019-05-07 | 2019-05-09 | Please Select...
19/YH/0093 | 255567 | HRA | A Randomized Open-Label, Phase 1b Study of the Safety of Pirfenidone Solution for Inhalation (AP01) in Patients with Idiopathic Pulmonary Fibrosis (ATLAS Study) | 2019-04-24 | No |  | 85 |  |  | 2019-04-10 | 2019-04-24 | 2019-06-04 | 2019-07-02 | 2019-07-18 | 2019-11-05 | Neither
19/YH/0100 | 260086 | HRA | A single arm, open-label clinical trial of azithromycin in pulmonary sarcoidosis | 2019-04-30 | Yes | 2019-09-17 | 35 | 105 | 140 | 2019-04-30 | 2019-04-30 | 2019-05-30 | 2019-05-30 | 2019-06-04 | 2019-09-06 | Sponsor
17/LO/1170 | 219279 | HRA | A multi-center, double-blind, placebo-controlled Phase 2b study to evaluate the efficacy and safety of macitentan in subjects with heart failure with preserved ejection fraction and pulmonary vascular disease | 2019-01-11 | Yes | 2019-12-03 | 138 | 188 | 326 | 2019-01-10 | 2019-01-11 | 2017-08-02 | 2019-05-21 | 2019-05-29 | 2019-07-31 | Neither
17/EE/0368 | 213669 | HRA | STRESS-L: STudy into the REversal of Septic Shock with Landiolol (Beta Blockade) | 2019-07-18 | No |  | 98 |  |  | 2019-07-11 | 2019-07-18 | 2017-11-10 | 2019-10-17 | 2019-10-24 | 2019-12-05 | Sponsor
18/LO/1847 | 250494 | HRA | Randomized Controlled Trial of Lasmiditan Over Four Migraine Attacks | 2019-06-26 | Yes | 2020-01-22 | 106 | 104 | 210 | 2019-06-14 | 2019-06-26 | 2019-05-21 | 2019-09-26 | 2019-10-10 | 2019-10-17 | NHS Provider
19/EE/0185 | 260536 | HRA | FIRST-line support for Assistance in Breathing in Children (FIRST-ABC): A master protocol of two randomised trials to evaluate the non-inferiority of high flow nasal cannula (HFNC) versus continuous positive airway pressure (CPAP) for non-invasive respiratory support in paediatric critical care | 2019-07-10 | Yes | 2019-12-02 | 98 | 47 | 145 | 2019-07-05 | 2019-07-10 | 2019-07-26 | 2019-10-09 | 2019-10-16 | 2019-11-07 | Sponsor
19/EM/0258 | 266702 | HRA | A randomised controlled trial of full milk feeds versus intravenous fluids with gradual feeding for preterm infants (30-33 weeks gestational age) | 2019-09-18 | No |  | 63 |  |  | 2019-07-17 | 2019-09-18 | 2019-09-13 | 2019-11-11 | 2019-11-20 | 2019-11-21 | Sponsor
19/LO/0803 | 263749 | HRA | A 12-month prospective, randomized, interventional, global, multi-center, active-controlled study comparing sustained benefit of two treatment paradigms (erenumab qm vs. oral prophylactics) in adult episodic migraine patients | 2019-09-27 | No |  | 32 |  |  | 2019-06-10 | 2019-09-27 | 2019-09-27 | 2019-10-12 | 2019-10-29 | 2019-10-30 | NHS Provider
19/NE/0152 | 260824 | HRA | "A Double-blind, Randomized, Placebo-controlled, Multicenter Study to Evaluate the Impact of Evolocumab on Major Cardiovascular Events in Patients at High Cardiovascular Risk Without Prior Myocardial Infarction or Stroke" | 2019-06-04 | Yes | 2019-11-27 | 71 | 105 | 176 | 2019-05-16 | 2019-06-04 | 2019-06-18 | 2019-08-07 | 2019-08-14 | 2019-10-07 | NHS Provider
19/SC/0034 | 254823 | HRA | A Phase 3, randomized, double-blind, parallel-group, placebo controlled multicenter study to evaluate the efficacy and safety of two doses of GLPG1690 in addition to local standard of care for minimum 52 weeks in subjects with idiopathic pulmonary fibrosis. | 2019-02-11 | Yes | 2019-10-09 | 205 | 35 | 240 | 2019-01-24 | 2019-02-11 | 2019-04-29 | 2019-08-26 | 2019-09-04 | 2019-09-11 | Please Select...
19/SW/0137 | 268815 | HRA | "A Phase 3, Randomized, Open Label Study to Compare Nivolumab plus Concurrent Chemoradiotherapy (CCRT) followed by Nivolumab plus Ipilimumab or Nivolumab plus CCRT Followed by Nivolumab vs CCRT followed by Durvalumab in Previously Untreated, Locally Advanced Non-small Cell Lung Cancer (LA NSCLC)" | 2019-08-05 | No |  | 119 |  |  | 2019-05-10 | 2019-08-05 | 2019-09-03 | 2019-12-02 | 2019-12-02 | 2019-12-04 | Both
19/SC/0311 | 262176 | HRA | Primary Antibiotic prophylaxis using co-trimoxazole to prevent SpontanEous bacterial PeritoniTIs in Cirrhosis (ASEPTIC) Primary Antibiotic prophylaxis using co-trimoxazole to prevent SpontanEous bacterial PeritoniTIs in Cirrhosis (ASEPTIC) | 2019-07-17 | No |  | 97 |  |  | 2019-06-25 | 2019-07-17 | 2019-08-07 | 2019-10-03 | 2019-10-22 | 2019-11-26 | NHS Provider
18/WA/0199 | 108978 | HRA | A randomised, placebo controlled trial of azithromycin for the prevention of chronic lung disease of prematurity in preterm infants | 2019-05-08 | Yes | 2019-10-19 | 146 | 18 | 164 | 2019-05-08 | 2019-05-08 | 2018-06-29 | 2019-09-12 | 2019-10-01 | 2019-10-04 | Neither
18/EE/0389 | 235758 | HRA | SPRING - Seizure PRophylaxis IN Glioma | 2019-08-21 | No |  | 124 |  |  | 2019-08-21 | 2019-08-21 | 2019-04-30 | 2019-12-23 | 2019-12-23 | 2020-01-13 | Please Select...
18/EM/0281 | 251974 | HRA | Long-term extension trial in subjects with atopic dermatitis who participated in previous tralokinumab trials – ECZTEND | 2019-10-23 | No |  | 90 |  |  | 2019-10-08 | 2019-10-23 | 2018-11-14 | 2020-01-07 | 2020-01-21 | 2020-01-21 | Sponsor
18/NS/0145 | 254786 | HRA | A NON-INTERVENTIONAL, MULTICENTER, MULTIPLE COHORT STUDY INVESTIGATING THE OUTCOMES AND SAFETY OF ATEZOLIZUMAB UNDER REAL-WORLD CONDITIONS IN PATIENTS TREATED IN ROUTINE CLINICAL PRACTICE | 2019-11-20 | No |  | 50 |  |  | 2019-10-08 | 2019-11-20 | 2019-02-07 | 2019-12-18 | 2020-01-09 |  | Please Select...
19/LO/0343 | 255538 | HRA | The PRECISE Protocol: Prospective Randomized Trial of the Optimal Evaluation of Cardiac Symptoms and Revascularization | 2019-12-03 | No |  | 8 |  |  | 2019-11-08 | 2019-12-03 | 2019-08-12 | 2019-12-06 | 2019-12-11 | 2020-01-24 | Please Select...
19/LO/0546 | 250345 | HRA | Effectiveness and cost-effectiveness of inspiratory muscle training (IMT) for reducing postoperative pulmonary complications (PPC): a sham-controlled randomised controlled trial (RCT) (INSPIRE) | 2019-09-26 | No |  | 55 |  |  | 2019-08-14 | 2019-09-26 | 2019-05-16 | 2019-11-11 | 2019-11-20 |  | Sponsor
19/LO/1381 | 257176 | HRA | "A Phase 4, Randomized, Double-blind, Placebo-controlled, Parallel-group Study to Evaluate the Efficacy and Safety of Erenumab in Adults With Chronic Migraine and Medication Overuse Headache" | 2019-10-29 | No |  | 35 |  |  | 2019-06-25 | 2019-10-29 | 2019-10-29 | 2019-10-24 | 2019-12-03 | 2019-12-18 | Both
19/NE/0215 | 234453 | HRA | "Frailty-adjusted therapy in Transplant Non-Eligible patients with newly diagnosed Multiple Myeloma: A phase III trial to compare standard and frailty-adjusted induction therapy with ixazomib, lenalidomide and dexamethasone (IRD) and maintenance lenalidomide (R) to lenalidomide plus ixazomib (R+I). " | 2019-11-07 | No |  |  |  |  | 2019-09-23 | 2019-11-07 | 2019-11-07 |  |  |  | Please Select...
19/NE/0346 | 263581 | HRA | A machine learning approach to quantitative stress echocardiography in new onset chest pain | 2019-11-13 | Yes | 2019-11-22 | 5 | 4 | 9 | 2019-11-12 | 2019-11-13 | 2019-11-11 | 2019-11-14 | 2019-11-18 | 2019-11-18 | Please Select...
19/NW/0317 | 262846 | HRA | "A Phase 2, Double-blind, Randomized, Placebo-controlled, Two-Treatment, Two-Period Crossover Efficacy and Safety Study in Idiopathic Pulmonary Fibrosis with Nalbuphine ER Tablets for the Treatment of Cough" | 2019-08-19 | No |  | 57 |  |  | 2019-08-19 | 2019-08-19 | 2019-07-12 | 2019-10-11 | 2019-10-15 |  | Both
19/SC/0122 | 259342 | HRA | A Randomized, Double-Blind, Placebo-Controlled Study of Diazoxide Choline Controlled-Release Tablet (DCCR) in Patients with Prader-Willi Syndrome | 2019-10-02 | Yes | 2019-12-17 | 55 | 21 | 76 | 2019-09-11 | 2019-10-02 | 2019-05-07 | 2019-11-26 | 2019-11-26 | 2019-12-05 | Sponsor
19/SW/0192 | 264531 | HRA | Augmented Reality Neuro Navigation System | 2019-06-03 | No |  | 227 |  |  | 2019-05-07 | 2019-06-03 | 2019-10-24 | 2020-01-16 | 2020-01-16 | 2020-01-16 | Neither
19/YH/0230 | 264808 | HRA | A Randomized, Double-blind, Placebo-controlled, Parallel Group, Multicenter, Phase 2a Study to Explore the Efficacy and Safety of Tezepelumab in Patients with Moderate to Very Severe Chronic Obstructive Pulmonary Disease (COPD) (COURSE) | 2019-11-11 | No |  | 11 |  |  | 2019-08-20 | 2019-11-11 | 2019-09-05 | 2019-11-18 | 2019-11-22 | 2020-01-02 | NHS Provider
19/EM/0101 | 260487 | HRA | Randomized, Double-Blind, Placebo-Controlled, Dose-Ranging, Efficacy and Safety Study with Inhaled RVT-1601 for the Treatment of Persistent Cough in Patients with Idiopathic Pulmonary Fibrosis (IPF): SCENIC Trial | 2019-03-14 | No |  | 187 |  |  | 2019-03-13 | 2019-03-14 | 2019-06-17 | 2019-06-12 | 2019-09-17 | 2019-09-17 | Neither